## Sep 2021
2021-09-01 | Pendle Leisure Trust Capital Works 2021 / 2022 | DRAFT PROPOSALS
C2B14CD14
Costs
Site | Works | Progress | Committed | LPS Fee £ | Total Project Cost £ | Comments
Proposed
Pendle Leisure Centre | Control Panel Replacement | surveyed awaiting price | 40000 | 4000 | 44000 | on hold - review with Trend/ PLT
Pendle Leisure Centre | Roof replacement - phased ?? Phase 1 £80k Phase 2 £ 100k |  | 80000 | 8000 | 88000 | sports hall roof is priority due to age and condition and can be completed in isolation
| Phase 2 |  | 100000 | 10000 | 110000 | phase 2
Pendle Leisure Centre | Emergency Lighting failure to pool side - replace CBU | Catchpoint report | 2627.25 | 341.5425 | 2968.7925 | Central Battery unit failed due to obsolscence - building is non compliant
| Additional CBU works for above | Catchpoint report | 1871 | 243.23 | 2114.23 | additional works
Pendle Leisure Centre | Minor works to car park / entrance pathway |  | 3500 | 455 | 3955 | Health and safety - slips, trips and falls
Wavelengths | Control Panel Replacement | surveyed awaiting price | 40000 | 4000 | 44000 | on hold - review with Trend / PLT
Wavelengths | Minor works to car park surface and forecourt pavers |  | 2000 | 260 | 2260 | Health and Safety - trip hazards / pot holes / surface degredation
Wavelengths | Rebuild wall / fence and barrier to parapet boundary wall in service car park |  | 19000 | 2280 | 21280 | Health and Safety - wall is overturning and may fall into back street . This is in dangerous condition.
Wavelengths | Service car park - re- surface entrance area |  | 11000 | 1320 | 12320 | surface has failed and requires concrete apron re-casting
Wavelengths | Wetside boiler replacement | reported on service / temp repair completed | 18000 | 2160 | 20160 | temp repair completed - no guarantee
West Craven Leisure Centre | Replace cladding to gym dormer frontage + installation of input / extract to roof void to alleviate condensation issue |  | 10000 | 1200 | 11200 | Condensation and water ingress issues to roof void over gym area
West Craven Leisure Centre | Replace wet side boilers | feasibility completed | 35000 | 3500 | 38500 | possible air source heat pump solution?? - awaiting ENGIE survey cost
West Craven Leisure Centre | Learner pool - ceiling replacement |  | 45000 | 4500 | 49500 | damp / mould / failing ceiling tiles - tiles no longer available - new / altered grid required
West Craven Leisure Centre | Dry side changing - ceiling replacement |  | 10000 | 1200 | 11200 | damaged / failing tiles - tiles no longer available - new / altered grid required
Municipal Hall | Works to tower structure and roof | Works approved | 55000 | 5500 | 60500 | on site
Municipal Hall | Inner quadrangle - re-render and associated repairs | awaiting price | 29193.75 | 2919.375 | 32113.125 | price confirmed
Municipal Hall | Dry Rot works | Stoneaoak | 7000 | 840 |  | Works ordered due to dry rot outbreak - awaiting confirmation of capital | ****
Marsden Golf Club | Entrance driveway - minor works to road surface |  | 2500 | 325 | 2825 | access driveway is severely pot holed - surface breaking up. Health and safety issue - slips, trips and falls
|  | 20202021 Committed works | 176498.25 | 18604.7725 | 195103.0225
|  | Additional priority works | 335193.75 | 34439.375 | 361793.125
Fee Charge
13% fee charged £0 - £4999
12% fee charged £5000 - £25000
Alarm Installations / Battery Renewals/Emergency Lighting / Pump replacements etc
£75 fee for inspection / sign off and submission of paper work H and S. etc
AHU installations - where no design input 10%
Control Panel Works - where no design input 10%
Emergency Lighting- 10% -where no design input
Works over £ 25k TBC

## Sheet1
Pendle Leisure Trust Capital Works 2021 / 2022
C2B14CD14
|  | Costs |  | Total
Site | Works | Proposed | LPS Fee £ | Project Cost | Reasoning behind investment required | Benefit
Pendle Leisure Centre | Control Panel Replacement | 40000 | 4000 | 44000 | If the panel fails then the facility cannot operate as the contol panel controls the plant | Facility can remain open/operate and the plant remains operational
Pendle Leisure Centre | Roof Replacement Phase 2 | 100000 | 10000 | 110000 | Roof leaking across all parts of the facility. PLT investing money in new equipment and actviities and ensuring inside is fit for purpose. Landlord responsibility. Potential claims | To protect and maintain the fabric of the building and extend the lifespan of the building
plus it's a health and safety issue and there is ongoing damage to the fabric of the building
Wavelengths | Control Panel Replacement | 40000 | 4000 | 44000 | If the panel fails then the facility cannot operate as the contol panel controls the plant | Facility can remain open/operate and the plant remains operational
Wavelengths | Service car park - re- surface entrance area | 11000 | 1320 | 12320 | Surface has failed and requires concrete apron re-casting. Dangerous. Not fit for purpose | Prevent any injury / damge and potential claims
Wavelengths | Wetside boiler replacement | 18000 | 2160 | 20160 | Temp repair completed - no guarantee. If the boliers fail then the pool cannot open | Facility can remain open/operate and the plant remains operational
West Craven Leisure Centre | Replace wet side boilers | 35000 | 3500 | 38500 | At the end of their useful life. If they fail then the Pools cannot open | Facility can remain open/operate and the plant remains operational
West Craven Leisure Centre | Learner pool - ceiling replacement | 45000 | 4500 | 49500 | Damp/mould/failing ceiling tiles. Tiles no longer available new/altered grid required. Ceiling is deteriorating. Potential for collapse of ceiling. Potential claim | To protect and maintain the fabric of the building and extend the lifespan of the building
West Craven Leisure Centre | Dry side changing - ceiling replacement | 10000 | 1200 | 11200 | Damp/mould/failing ceiling tiles. Tiles no longer available new/altered grid required. Ceiling is deteriorating. Potential for collapse of ceiling. Potential claim | To protect and maintain the fabric of the building and extend the lifespan of the building
Municipal Hall | Inner quadrangle - re-render and associated repairs | 29193 | 2919 | 32113 | Water ingress as render has fallen off. Deterirotion of the structure and fabric of the building. Scaffolding already in place for work to be carried out | To protect and maintain the fabric of the building and extend the lifespan of the building
Municipal Hall | Dry Rot works | 7000 | 840 | 7840 | Works required to stop the spread to other parts of the building and mitigate any further damage to the structure and fabric of the building | To protect and maintain the fabric of the building and extend the lifespan of the building
| Additional Priority Works | 335193 | 34439 | 369633