## Slide 1: Recap: LGR so far
Our priority has been engaging with areas and laying the necessary legislation to get the LGR ball rolling; now we will begin to work through proposals with individual areas and Govt departments
Dec 2024
Jan - Feb
March onwards
December 2024
Published the English Devolution White Paper
Letters to councils setting out next steps and what to expect
Engagement – with councils and across government
Our focus in early 2025 has been:
Statutory invitations and announcement – letters to councils with the criteria for reorganisation
Delaying elections – deadlines for requests from councils, decisions from Ministers, legal activity started
Engagement – with councils, the sector and representative bodies, trade unions, OGDs
March onwards
Interim plans due from areas before 21 March
Analysis of proposals and ongoing discussion with areas and across government
May: LGR proposals due from Surrey
September: LGR proposals due from DPP areas
November: LGR proposals from other areas
Written statements - Written questions, answers and statements - UK Parliament

## Slide 2: Statutory invitation letter - Key points
Where this is not possible, Government will consider any suitable proposals submitted
Leaders to work together to develop a proposal that best meets local needs
Letter to leaders of all councils in two-tier areas, districts and counties, and neighbouring unitaries
Summarising the broad approach to LGR set out in the letter
Clear aspiration that there will be one agreed proposal for each area

## Slide 3: Assessment criteria
Meet local needs and be informed by local views
Prioritise the delivery of high quality and sustainable public services
Reorganisation proposals should seek to achieve for the whole of the area concerned the establishment of a single tier of local government:
Be the right size to achieve efficiencies, improve capacity and withstand financial shocks (population of 500,000 or more)
Criteria against which proposals will be assessed in coming to a decision on implementation
Support devolution arrangements
Enable stronger community engagement and neighbourhood empowerment

## Slide 4: Local engagement
It is for councils to decide how best to engage locally and provide evidence of that activity in proposals
Proposals should consider issues of local identity, and cultural and historic importance, ensuring ceremonial rights and privileges can be maintained
For those areas where Commissioners have been appointed by the Secretary of State as part of a Best Value Intervention, their input will be important in the development of robust unitary proposals
Ensuring that proposals are informed by local views
The views of other public sector providers will be crucial, including:
the relevant Mayor
Integrated Care Board
PCC/PFCC/Fire and Rescue Authority
Higher Education and Further Education providers
National Park Authorities
Voluntary and third sector
Local Members of Parliament
Town and parish councils

## Slide 5: Proposal submission dates
Any proposal due 28 November
Go-live 2028
Local elections as scheduled
All other areas
Any proposal due 9 May
Go-live 2027
Local elections postponed
Surrey
Any proposal due 26 September
Mayoral election in May 2026
Go-live 2028
Local elections postponed
DPP areas
. Response to invitation sent to all councils – districts, counties, unitaries
(actual go-live dates dependent on proposals received)
Essex (Southend, Thurrock)
Hampshire (IoW, Portsmouth, Southampton)
East Sussex (Brighton) & West Sussex
Norfolk & Suffolk
Cambridgeshire (Peterborough)
Derbyshire (Derby City)
Devon (Plymouth, Torbay)
Gloucestershire
Hertfordshire
Kent (Medway)
Lancashire (Blackburn with Darwen, Blackpool)
Leicestershire (Leicester City)
Lincolnshire (NE Lincs, N Lincs)
Nottinghamshire (Nottingham City)
Oxfordshire
Staffordshire (Stoke on Trent)
Warwickshire
Worcestershire

## Slide 6: Indicative LGR Timelines for Surrey, DPP & all other 2-tier areas Potential planning assumptions for ambitious timetabling. Actual timings will be dependent on proposals received
 | Surrey LGR |  | Elections
 | DPP devo |  | LGR – DPP and other 2 tier areas
January - April 2025 | May - August 2025 | September - December 2025
January - April 2026 | May - August 2026 | September - December 2026
April 2027 | May - December 2027 | April 2028
May 26 local elections
Shadow unitary elections (as soon as possible)
DPP CCA decisions post consultation
Any transitional legislation for Surrey unitary(s)
Govt receives LGR proposals from DPP areas (26 Sept)
Mayoral election to CCA (DPP)
New unitaries Go-live
Government consults on Mayoral devolution (Feb – Apr)
Govt. issues statutory invite for LGR proposals (5 Feb)
DPP CCA legislation laid with local consent
Government receives interim LGR plan from all areas (21 March)
Govt consults on Surrey LGR proposal(s)
Govt receives Surrey LGR proposal(s) (9 May)
Govt receives final LGR proposals from other 2-tier areas (28 Nov)
Consultation on other 2-tier area LGR proposals
Govt. decision on Surrey LGR proposal(s)
Surrey LGR legislation laid
Election for Surrey ‘Shadow’ Unitary(s)
CCA legislation approved by parliament and legislation in force (DPP)
LGR legislation approved for Surrey
Govt. decision on DPP LGR proposals
Govt decision on proposals for other 2-tier areas following consultation
LGR legislation prepared and laid for DPP and other 2-tier areas
Surrey Unitary(s) Go-live (April)
May 25 local elections
Any transitional legislation needed prepared and laid
Govt. announces final DPP areas (Spring)
Govt. publishes consultation results summary (Spring)

## Slide 7: Interim plans
The level of detail that is possible at this stage may vary from place to place
There is no template for the interim plans, it is entirely up to areas how they wish to present their initial thinking
Interim plan may describe more than one potential proposal for the area, if there is more than one option under consideration
Each area should submit an interim plan on or before 21 March 2025
Sets out progress on developing proposals in line with the criteria
Check-in point to show direction, momentum & assurance that councils working together
What needs to be included
To include:
size and boundaries of new councils
indicative costs and efficiencies
options for future service transformation opportunities
councillor numbers
supporting devolution
local engagement
indicative costs of implementing proposals and standing up an implementation team

## Slide 8: Support for areas
Will be more interested in content than glossy, expensive documents
What we don’t need
Invitation letter set out commitment to make available capacity resource for areas
Interim plans should set out indicative costs of implementing proposals and standing up an implementation team
Capacity resource
We recognise that reorganisation will create upfront costs and additional pressures for councils alongside their crucial responsibilities to communities
We have a collective responsibility to support councils in developing proposals and implementation plans to stand up new unitary councils ready for vesting day
Continuing BAU activity
Ensuring areas are supported throughout the reorganisation process
Sector support
MHCLG engaging closely with a range of sector bodies to plan how best to support councils through this process
These include LGA, the District Councils Network, the County Councils Network, CIPFA and others
Commitment to learn from the experience and successes of those who have been through the process