| Report Title | Area Committee Budget 2025/26 |
| --- | --- |
| Meeting | Nelson, Brierfield & Reedley Committee |
| Meeting Date | 3 November 2025 |
| Report Author | Julie Mousdale |
| Directorate | Resources |
| Lead Executive Member(s) | Leader Portfolio |
| Wards Affected | Bradley, Brierfield East and Clover Hill, Brierfield West and Reedley, Marsden and Southfield, Whitefield and Walverden |
| Public. Part Exempt, or Fully Exempt | Public |
| Appendices (if any) | Appendix 1: Budget Table (spend up to 13/10/25) |

- Executive Summary

  - The budget for 2025/26 is £78,270 plus £63,161 carried forward from the previous year. Therefore, the total funds made available for 2025/26 is £141,431. All of this has been committed to various schemes.

- Recommendations

For the reasons set out in this report, NELSON, BRIERFIELD & REEDLEY COMMITTEE is recommended to:

  - Note the budget as committed. See appendix 1.

  - Note the financial implications stipulated in paragraph 6:4.

- Information: the Rationale & Evidence for the Recommendations

  - To enable the committee to allocate its budget effectively and in line with financial regulations.

- Link to Council Plan Priorities: (Providing High Quality Services and Facilities, Proud and Connected Communities and Places, Good Growth and Housing and Healthy Communities)

  - Providing High Quality Services and Facilities - this report shows the current budget position which enables Nelson, Brierfield and Reedley Committee to make informed decisions when allocating its money to schemes.

- Implications (see Items 6 – 10)

- Financial Implications

  - Awards can be made for schemes which are either revenue or capital in nature so there could be revenue consequences of capital schemes in terms of ongoing cost.

  - Schemes may incur additional charges for internal services, e.g. Engineers’ costs in delivering the scheme.

  - Schemes should be completed and payment made by 31 March. Any slippage will need to be agreed by the Council in line with Financial Regulations.

  - The maximum carry-forward figure is £78,270 as it is capped at the equivalent of 1 year’s budget. If the committee have more than £78,270 unspent at the end of the year it will need to use the following year’s budget to make up the difference.

- Legal and Governance Implications

  - There are legal implications relating to some schemes in terms of necessary permissions, agreements and possible long-term liabilities and responsibilities.

- Climate and Biodiversity Implications

  - There are no climate and biodiversity implications from the recommendations.

- Human Resources Implications

  - There are no human resources implications from the recommendations.

- Equality and Diversity Implications

  - There are no equality and diversity implications from the recommendations.

- Consultation

  - n/a

- Alternative Options Considered

  - n/a

- Statutory Officer Sign Off (please put an x in the relevant box below)

| Section 151 Officer | X |
| --- | --- |
| Monitoring Officer | X |

- Background Documents

  - None

Contact Officers

Julie Mousdale, Democracy and Legal. Tel: 01282 661569

Email: julie.mousdale@pendle.gov.uk

Nelson, Brierfield and Reedley Committee Commitments 2025/26                                                                                  Appendix 1

(Shaded schemes are completed)

| Sch. No. | Scheme Details | Lead Officer/ Service Area | c/f from previous Years | Allocated 2025/26 | Total Allocation | In-Year Spend | Remaining | Status of Scheme/Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 2 | Nelson Cenotaph | S Whalley (EG) | 2,500 | 0 | 2,500 | 2,500 | 0 | Completed |
| 3 | Brunswick Street - Public Realm Improvements | S Whalley (EG) | 5,500 | 0 | 5,500 | 0 | 5,500 |  |
| 4 | 06/05/25 - £1,000 Litter and Dog Bins | J Lord (OS) | 138 | 1,000 | 1,138 | 589 | 549 | The spend may not be up to date. Operational Services report fully on this. |
| 6 | 03/04/25 - £15,000 Premises Improvement Grants | D McCarthy (EG) | 9,100 | 15,000 | 24,100 | 10,214 | 13,886 | The spend may not be up to date. Economic Growth report fully on this. |
| 8 | Refurbishment of Street Furniture at Nelson Town Centre | S Whalley (EG) | 1,500 | 0 | 1,500 | 0 | 1,500 |  |
| 9 | Gully Works to Unadopted Back Streets | S Whalley (EG) | 1,816 | 0 | 1,816 | 578 | 1,238 |  |
| 10 | 06/05/25 - £12,900 Bradley - Ward Projects |  | 9,130 | 12,900 | 22,030 | 1,000 | 21,030 | £1,000 spent - Pendle United |
| 11 | 06/05/25 - £12,900 Brierfield East and Clover Hill - Ward Projects |  | 9,130 | 12,900 | 22,030 | 0 | 22,030 |  |
| 12 | 06/05/25 - £8,590 Brierfield West and Reedley – Ward Projects |  | 6,087 | 8,590 | 14,677 | 0 | 14,677 |  |
| 13 | 06/05/25 - £12,900 Marsden and Southfield – Ward Projects |  | 9,130 | 12,900 | 22,030 | 0 | 22,030 | 04/08/25 - £5,000 committed to Marsden Park Pond Restoration. |
| 14 | 06/05/25 - £12,900 Whitefield and Walverden – Ward Projects |  | 9,130 | 12,900 | 22,030 | 0 | 22,030 |  |
| 15 | 06/05/25 - £80 FOVP – PL Insurance for events | R Oliver (FOVP) | 0 | 80 | 80 | 80 | 0 | Completed |
| 16 | 06/05/25 - £2,000 Pendle Cricket Tournament |  | 0 | 2,000 | 2,000 | 2,000 | 0 | Completed |
|  | Subtotal |  | 63,161 | 78,270 | 141,431 | 16,961 | 124,470 |  |
|  | Un-allocated Funds |  | 0 | 0 | £0 | - | £0 |  |
|  | Total Funds Available 2025/26 |  | 63,161 | 78,270 | 141,431 | 16,961 | 124,470 |  |